## history
Date
●Revision history |  |  |  | KSMT Designer
KSMT Approve
Date | Sheet | Description of Change | Sign
2026-08-14 |  | Eric provide placement modify; version:V2
2026-08-17 |  | Eric provide placement modify; version:V3
2026-08-25 |  | Eric provide modify; version:V4
2026-08-25 |  | Eric provide modify; version:V5,item 17/18
2026-08-28 |  | Eric provide modify; version:V6
2026-09-02 |  | Eric provide modify; version:V7
2026-09-04 |  | Eric provide modify; version:V8
2026-09-04 |  | Eric provide modify; version:V9
2026-09-05 |  | Eric provide modify; version:V10
2026-09-09 |  | Eric provide modify; version:V11
2026-09-11 |  | Eric provide modify; version:V12

## schematic
Response
| S.No | Date | Sign | Status | Note | Link | ITEST REPLY | LINK
close | 1 | 2026-08-06 |  |  | xtal close to dut，please notice schematic text | xtal
close | 2 | 2026-08-06 |  |  | placement: Xtal -> RX/TX relay -> Flash -> AUX
close | 3 | 2026-08-06 |  |  | EDP RX route top，diff 85 | EDP
close | 4 | 2026-08-06 |  |  | OLV RX / ELV RX / iSP TX/ Mini LVDS TX/ LVDS TX Diff 100 Dut to relay route L28/L30/L32 Relay to PS1600 route L3/L5/L7 |  | Completed | #4
close | 5 | 2026-08-06 |  |  | Power note | PWR
close | 6 | 2026-08-06 |  |  | Assign please follow rule | rule
close | 7 | 2026-08-06 |  |  | High speed Layout need Gnd via TX/TX/AUX/xtal need Gnd shielding | Gnd | Completed | Gnd
close | 7-1 | 2026-09-02 |  |  | modify fan out | 7-1 | Completed | 7-1
close | 8 | 2026-08-14 |  |  | I2C&Flash modify | I2C modify
close | 9 | 2026-08-14 |  |  | debug modify | debug hole'
close | 10 | 2026-08-14 |  |  | TX/RX relay modify | relay | Completed | relay
close | 11 | 2026-08-17 |  |  | Some power relays can be place on the right side. | pwr relay
close | 12 | 2026-08-25 |  |  | relay fan out modify | Gnd via | Completed | Gnd via
close | 13 | 2026-08-25 |  |  | ISP TX length is too long. Please shorten the trace length. Assign 16 relays each for Site 1 and Site 2, moving upward. | assign | Completed | assign
close | 14 | 2026-08-25 |  |  | TX/RX relay remove the pad copper with reference to the L31 GND layer. TX/RX Device remove the pad copper with reference to the L4 GND layer. | pad | Completed | pad
close | 15 | 2026-08-25 |  |  | High speed Layout need Gnd shielding | shielding | Completed | shielding
close | 16 | 2026-08-25 |  |  | TX/RX should first be length-matched for P/N separately on each layer: L3/L5/L7/L28/L30/L32. Then adjust the overall length, preferably along the relay-to-pogo path. |  | Completed | #16
close | 17 | 2026-08-25 |  |  | *K43 relay fan out modify | K43 | Completed | K43
close | 18 | 2026-08-25 |  |  | The routing between DUT and the relay should be optimized by swapping the relay positions based on the fan-out arrangement to minimize the trace length. | swap relay | Completed | swap relay
close | 19 | 2026-08-28 |  |  | Only excavate the pad area according to the pad size. |  | Completed | #19
close | 20 | 2026-08-28 |  |  | Point 10 has not been updated yet. |  | Completed | relay
close | 21 | 2026-08-28 |  |  | The trace from 4K43 to 4K1 is too long. |  | Completed | #20
close | 22 | 2026-08-28 |  |  | High-speed vias should be surrounded by GND vias and should not be placed without GND via shielding. | high-speed via | Completed | high-speed via
close | 23 | 2026-09-02 |  |  | Please swap the SENSE and GND SENSE connections. The L15 power trace is too narrow and needs to be widened. Also, please increase the clearance around the capacitors to avoid any physical interference or damage. | l15-pwr | Completed | l15-pwr
close | 24 | 2026-09-02 |  |  | Would it be better to swap the red and yellow power routing? For the left side, please use the same SENSE connection points for Site 1 and Site 3, and copy the same layout pattern near the socket. Please apply the same approach to Site 2 and Site 4 as well. | l15-pwr-swap | Completed | l15-pwr-swap
close | 25 | 2026-09-02 |  |  | Please modify L20 according to Item 23 and increase the spacing between the capacitors. | L20-pwr | Completed | L20-pwr
close | 26 | 2026-09-02 |  |  | Please minimize unnecessary routing. The power routing between the left and right sites should be kept reasonably symmetrical. Please also make the upper and lower site layouts as identical as possible. Please add additional copper shape channels similar to the yellow shape to improve the routing path. | L22-pwr | Completed | L22-pwr
close | 27 | 2026-09-02 |  |  | For L24, please check whether the red and yellow power routing should be swapped. Please apply the same approach to Site 3. The SENSE connection points should be kept consistent. | L24-pwr | Completed | L24-pwr
close | 28 | 2026-09-04 |  |  | Move the purple shape from L20 to L17 or L18, and add a yellow shape in the routing channel inside the DUT. | L20-pwr-1 | Completed | L20-pwr-1
close | 29 | 2026-09-04 |  |  | Please route the Sense signals so that Site 1 and Site 3 connect to the same point, and Site 2 and Site 4 connect to the same point. Also, please connect them to the power via at the end of the shape and the nearby GND via. |  | Site 1 and Site 3, Site 2 and Site 4 sense connections connected to the same points. Power via connected to the end of the shape | #29
close | 30 | 2026-09-04 |  |  | Please route all the power connections on L17 using power shapes. For any areas where the 5V connection cannot be reached directly, please connect them through other layers. Make sure there is a GND shape between the power and 5V. |  | Completed | L17
close | 31 | 2026-09-04 |  |  | Please increase the width of the power traces on L20. This has not been fixed yet. |  | Completed | L20
close | 32 | 2026-09-07 |  |  | Please modify the AUX resistors according to the figure below. | AUX R | Completed | AUX R
close | 33 | 2026-09-07 |  |  | Please add GND vias near the AUX signal layer transition vias. | AUX GND | Completed | AUX GND
close | 34 | 2026-09-09 |  |  | Please increase the power shape channel width for CSDPS225P9 and CSDPS425P4. | pwr-1 | Completed | pwr-1
open | 35 | 2026-09-11 |  |  | We found some nets that were assigned multiple times in the length-matching table. Please correct the duplicated net assignments and update the length-matching table accordingly. Also, the current layout has over 30,000 traces that are excessively long. Please review the routing and optimize the trace lengths where possible. | assign-1 | Completed and routing optimized | assign-1

## #29 (hidden)
ITEST

## L20 (hidden)
ITEST

## L17 (hidden)
ITEST

## L20-pwr-1 (hidden)
ITEST

## AUX R (hidden)
ITEST

## AUX GND (hidden)
ITEST

## pwr-1 (hidden)
ITEST

## assign-1
iTEST

## Gnd (hidden)
ITEST

## 7-1 (hidden)
ITEST

## l15-pwr (hidden)
ITEST

## l15-pwr-swap (hidden)
ITEST

## L20-pwr (hidden)
ITEST

## L22-pwr (hidden)
ITEST

## L24-pwr (hidden)
ITEST

## I2C modify (hidden)
You can place it a bit further away from the DUT.

## debug hole (hidden)
This can be placed in the open spaces on either the left or right side.

## relay (hidden)
Please place the relay within the orange box, minimizing the length of the path from the DUT to the relay and then to the PS1600.
Configure the relay fan-out as shown in the diagram below.
ITEST

## assign (hidden)
ITEST

## Gnd via (hidden)
ITEST

## pad (hidden)
ITEST

## shielding (hidden)
ITEST

## K43 (hidden)
ITEST

## swap relay (hidden)
ITEST

## high-speed via (hidden)
ITEST

## #4 (hidden)
ITEST
DUT TO RELAY
| L28,L30,L32 | RELAY TO POGO
L3,L5,L7

## #16 (hidden)
ITEST

## #19 (hidden)
ITEST

## #20 (hidden)
ITEST